## Slide 1: Master Plan
Updated 2023 06 17

## Slide 2: Goal
07/2023 - 07/2027 (4 years, covering 8th, 9th, 10th and 11th grade)
Publish 2+ conference papers
Publish 1+ journal paper
Attend 2+ conference and present papers
Lead and organize one session in 2025 international conference (International electrical machine and Drive conference, IEMDC), Half participants is from outside of US.
Collaborate with 1+ industrial partners
Collaborate with 1+ academic partners

## Slide 3: Master Plan
2023.07 - 2023.12:
  Basic knowledge of motor and AI
  Literature study of current research status by reading and summarizing 50+ papers
  Define the first research topic
  Build a simple test bed based on AWS.
2024.01 - 2024.06
  Complete the first research topic
  Complete experiments for the first research topic
  Submit the first conference paper

## Slide 4: Collaboration
Use Github for document sharing.
  Most will codes based. So, code management is important.
  Both Yao and I can access the documents everywhere
Literature management
  Zotero
Paper writing tools
  TBD. Microsoft words preferred.

## Slide 5: Plan for 6/18 – 6/25
Set up the Github for Wendy and Yao. – By David and Wendy.
Introduction for motor. – By Yao
Find 10 papers. – By Peter